## Phase Gates
PA / milestone | Phase | Due | Proposed exit criteria
PA1 | Initiation & planning | End of Week 3 | Vision and scope agreed; Must/Should/Could/Won't priorities documented; WBS contains at least three levels; work packages have owners, estimates and due dates; schedule, critical path, roles, risks, tool setup and AI usage log documented.
PA2 | Requirements | End of Week 5 | SRS reviewed by the team; functional requirements numbered and prioritised; measurable non-functional requirements and domain rules documented; use-case model/specifications, mockups, acceptance criteria and traceability prepared.
PA3 | Design | End of Week 7 | Architecture and design consistent with PA2; C4 context/container and other required design models completed; data and UI designs reviewed; architecture decisions recorded; requirement changes listed.
PA4 | Test planning | End of Week 8 | Test plan, test cases and test data prepared; applicable EP/BVA/decision-table techniques documented; Must-have requirements traced to tests; test environment, entry/exit criteria and defect process agreed.
PA5 | Implementation, testing & deployment | End of Week 10 | Must-have features implemented; unit and automated tests run; system-test results and defects recorded; CI and deployment evidence available; setup instructions and implementation/test report completed.
Final | Presentation & demo | Week 11 | Presentation covers the project coherently; live demo demonstrates key scenarios; all members prepared to explain contributions and design decisions.

## WBS
WBS ID | Work package / deliverable | Owner (proposed from PA0 roles) | Dependency
1.0 | Project initiation and planning
1.1.1 | Confirm project scope and priorities | BA – Lê Đoàn Nhật Huy | PA0
1.1.2 | Complete PA1 project plan and review | Team lead – Huỳnh Trung Ngạn | 1.1.1
1.2.1 | Configure repository, protected main and README | Developer – Trương Hiển Long | PA0
1.2.2 | Configure board, task ownership and communication | Team lead – Huỳnh Trung Ngạn | PA0
2.0 | Requirements (PA2)
2.1.1 | Elicit teacher/student needs and clarify open questions | BA – Lê Đoàn Nhật Huy | 1.1
2.1.2 | Specify functional and non-functional requirements | BA – Lê Đoàn Nhật Huy | 2.1.1
2.2.1 | Prepare use cases, flows and acceptance criteria | BA – Lê Đoàn Nhật Huy | 2.1.2
2.2.2 | Prepare UI mockups and review against use cases | Designer – Trần Hoàng Minh Khang | 2.1.1
2.3.1 | Build traceability matrix and review SRS | Tester/BA – Lê Đoàn Nhật Huy | 2.2.1, 2.2.2
3.0 | Software design (PA3)
3.1.1 | Draft C4 context/container and architecture | Designer – Trần Hoàng Minh Khang | PA2 baseline
3.1.2 | Record architecture decisions (ADRs) | Designer – Trần Hoàng Minh Khang | 3.1.1
3.2.1 | Design data model and constraints | Designer – Trần Hoàng Minh Khang | PA2 baseline
3.2.2 | Design key screens and navigation | Designer – Trần Hoàng Minh Khang | 2.2.2
3.3.1 | Review design consistency and traceability | BA + Designer | 3.1, 3.2
4.0 | Test planning (PA4)
4.1.1 | Define test scope, levels, environment and exit criteria | Tester – Lê Đoàn Nhật Huy | PA3 baseline
4.1.2 | Design test cases and test data for Must-have features | Tester – Lê Đoàn Nhật Huy | 4.1.1
4.2.1 | Trace requirements to test cases and review test plan | Tester + BA | 4.1.2
5.0 | Implementation, testing and deployment (PA5)
5.1.1 | Set up application skeleton and configuration | Developer – Trương Hiển Long | PA3 baseline
5.1.2 | Implement authentication and authorisation | Developer – Trương Hiển Long | 5.1.1
5.2.1 | Implement course management | Developer – Trương Hiển Long | 5.1.1, 5.1.2
5.2.2 | Implement classroom activities/assignments | Developer – Trương Hiển Long | 5.2.1
5.3.1 | Run unit, integration and system tests; fix defects | Tester + Developer | 5.1–5.2
5.3.2 | Configure CI and deploy; verify setup instructions | Developer + Team lead | 5.3.1
5.4.1 | Prepare PA5 report and demo scenario | Team lead + Tester | 5.3.2
6.0 | Final presentation and demo
6.1.1 | Prepare slides, speaking parts and demo rehearsal | All members; lead coordinates | PA5
6.1.2 | Deliver final presentation and demo | All members | 6.1.1

## Estimation
WBS ID | Work package | Owner | Effort (person-hours) | Method / assumptions
1.1.1 | Confirm scope and priorities | BA | 4 | Expert judgement; PA0 is the starting point
1.1.2 | PA1 plan and review | Team lead | 8 | Includes coordination and peer review
1.2.1 | Repository setup and README | Developer | 3 | GitHub repository already identified in PA0
1.2.2 | Board and communication setup | Team lead | 3 | Existing Discord and GitHub Projects are used
2.1.1 | Elicit and clarify requirements | BA | 8 | Teacher/student workflows and open questions
2.1.2 | Specify functional/NFR requirements | BA | 12 | Must-have flows prioritised
2.2.1 | Use cases and acceptance criteria | BA | 10 | Includes main, alternative and exception flows
2.2.2 | UI mockups | Designer | 8 | Main Must-have scenarios
2.3.1 | Traceability and SRS review | Tester/BA | 5 | One team review cycle assumed
3.1.1 | Architecture diagrams | Designer | 8 | Initial architecture scope
3.1.2 | Architecture decision records | Designer | 4 | Proposed minimum of three ADRs, aligned with rubric
3.2.1 | Data model | Designer | 8 | Core users, courses and classroom activities
3.2.2 | Screen/navigation design | Designer | 6 | Based on PA2 mockups
3.3.1 | Design consistency review | BA + Designer | 4 | Includes traceability review
4.1.1 | Test plan and environment | Tester | 6 | Includes test levels and entry/exit criteria
4.1.2 | Test cases and data | Tester | 10 | Must-have features first
4.2.1 | Traceability and test review | Tester + BA | 4 | Review and corrections
5.1.1 | Application skeleton/configuration | Developer | 8 | Vue/Nuxt direction from PA0; final stack is still to be confirmed
5.1.2 | Authentication/authorisation | Developer | 20 | Assumes a basic role model and no complex institutional SSO
5.2.1 | Course management | Developer | 22 | Basic create/view/update/delete workflows as confirmed in PA2
5.2.2 | Classroom activities | Developer | 24 | Basic coursework/assignment workflows; rich upload/storage may be reduced if needed
5.3.1 | Test execution and defect fixing | Tester + Developer | 20 | Unit, integration and system testing
5.3.2 | CI and deployment | Developer + Lead | 8 | One deployment target; no high-availability setup
5.4.1 | PA5 report and demo scenario | Lead + Tester | 6 | Evidence and report preparation
6.1.1 | Presentation and rehearsal | All members | 8 | Shared preparation effort
6.1.2 | Final delivery | All members | 4 | Team presentation/demo preparation and delivery
| Total estimated effort |  | 231 | Planning estimate; revise as actuals become available

## Schedule
Week | Planned work | Milestone / dependency
Week 2 | Confirm PA0 baseline; initialise repository/board; begin PA1 | PA0 approval required before PA1 work proceeds
Week 3 | Complete scope, WBS, estimates, schedule, roles, risks and tool setup | PA1 due: end of Week 3
Week 4 | Elicit requirements; draft FR/NFRs, use cases and mockups | PA1 baseline
Week 5 | Complete SRS, acceptance criteria, traceability and review | PA2 due: end of Week 5
Week 6 | Architecture, data model, UI design and ADRs | PA2 baseline
Week 7 | Complete and review design models | PA3 due: end of Week 7
Week 8 | Test plan, test cases, data, traceability and review | PA4 due: end of Week 8
Weeks 8–9 | Implement Must-have features; integrate incrementally; run unit/integration tests | PA3 design and PA4 test plan are inputs; three-week implementation phase spans the end of Week 8 through Week 10
Week 10 | System testing, defect fixes, CI/deployment evidence, report | PA5 due: end of Week 10
Week 11 | Prepare and deliver final presentation and live demo | Final presentation/demo

## Milestones
Milestone | Description | Due
M1 | PA1 submitted | End of Week 3
M2 | PA2 SRS submitted | End of Week 5
M3 | PA3 design submitted | End of Week 7
M4 | PA4 test plan submitted | End of Week 8
M5 | PA5 implementation/testing/deployment submitted | End of Week 10
M6 | Final presentation and demo | Week 11

## Roles
Role | Main | Backup | Responsibilities
Team lead / Project manager | Huỳnh Trung Ngạn | Trương Hiển Long | Plan and assign tasks, track progress, coordinate reviews, act as contact point, collect weekly status reports and AI logs
Business analyst | Lê Đoàn Nhật Huy | Trần Hoàng Minh Khang | Elicit and document requirements, organise reviews, maintain requirement/acceptance criteria traceability
Designer / Architect | Trần Hoàng Minh Khang | Huỳnh Trung Ngạn | Architecture, class/data/UI design, design decisions and consistency reviews
Developer | Trương Hiển Long | Huỳnh Trung Ngạn; Lê Đoàn Nhật Huy | Implement features, write unit tests, review pull requests, support integration and deployment
Tester | Lê Đoàn Nhật Huy | Trần Hoàng Minh Khang | Test plan/cases, test data, system testing, defect reports and test traceability

## Cost Estimate
Category | Item | Planning assumption | Estimated cost (VND)
Labour | Project effort | 231 person-hours
Labour | Assumed junior-developer rate | 100,000 VND/person-hour
Labour | Labour-equivalent cost | 231 × 100,000 VND | 23100000
Non-labour | GitHub, GitHub Projects, Discord | Use existing/free tiers where sufficient | 0
Non-labour | Development tools | Use existing/free student tools | 0
Non-labour | Hosting/deployment | Free tier or student allowance; contingency if paid hosting is required | 1000000
Non-labour | Domain / other project costs | Optional; only purchase if needed for demo | 500000
Total | Estimated non-labour total |  | 1500000
Total | Total estimated project cost | Labour-equivalent + non-labour | 24600000

## Decisions to Confirm
No. | Decision to confirm before submission
1 | Confirm the final database choice (PA0 lists PostgreSQL, MongoDB or Firebase as possibilities).
2 | Confirm authentication, file-storage and deployment providers; these were open questions in PA0.
3 | Confirm whether assignments require file uploads in the Must-have scope; PA0 identifies rich uploads/storage as a project risk.
4 | Add exact calendar dates to task-board tasks when the official week calendar is available.
5 | Replace planning estimates with team-agreed estimates and track actual hours in weekly reports.
6 | Verify that each lowest-level WBS item has an owner, due date and task-board link.

## Assumptions & Notes
Category | Assumption / note
Process | The project follows the waterfall model; each PA submission serves as a phase gate and baseline; test planning follows the course's V-model approach.
Phase-gate rule | Team lead checks completeness before each submission; each document and PR is peer-reviewed by at least one other member.
Team | Four members, each targeting at least 15 hours per week as stated in PA0.
Scope | Implementation window is three weeks; Must-have scope must remain small and testable.
Stack | Vue with Nuxt is the current direction in PA0; database and deployment/storage/auth providers undecided.
Exclusions | Estimate excludes optional feature expansion, institution-level administration, live video, and private real-time chat.
Effort vs duration | Effort is not duration: work can overlap only when dependencies and available people allow it.
Schedule rule | Internal completion target is two days before each PA deadline; weekly status report due Sunday 23:59.
Meeting cadence | Internal team meeting: Saturday 20:15 online; weekly TA status meeting: Monday 20:15 online.
Cost caveat | Hourly rate and tool/hosting amounts are planning assumptions; labour-equivalent cost is not necessarily actual spend.